## Gap Assessment
Oscorp NIST CSF Gap Assessment
Derived from the GRC Mastery NIST Cyber Security Assessment (2026) and aligned to the Oscorp 1–5 risk register.
Gap ID | NIST Function | NIST Category | Control / Capability | Current State | Target State | Status | Current Maturity | Target Maturity | Maturity Gap | Related Risk ID | Recommended Action | Priority | Responsible Owner | Roadmap Phase | Business / Security Rationale
GAP-001 | Identify | Asset Management | Physical asset inventory coverage | A CMDB exists, but it should be expanded to include all hardware and a regular update schedule is not established. | CMDB should comprehensively cover in-scope hardware and be reviewed on a defined schedule. | Partial | 2 | 3 | 1 | R-003 | Expand the CMDB to network equipment, servers, endpoints, and other in-scope hardware; establish ownership and recurring reconciliation. | High | IT Operations | Year 1 – Q2 | Existing capability reduces implementation effort, but incomplete coverage creates blind spots.
GAP-002 | Identify | Asset Management | Software and SaaS inventory | SaaS applications are used, but local applications and SaaS instances are not comprehensively catalogued or reviewed. | Maintain an authoritative software/SaaS inventory with owners, criticality, sensitivity, and recurring review. | Fail | 1 | 3 | 2 | R-003 | Inventory software, SaaS, and critical applications; assign owners and classifications; reconcile on a defined schedule. | High | IT Operations | Year 1 – Q2 | Unknown software limits patching, access governance, monitoring, and recovery.
GAP-003 | Identify | Asset Management | Network and data-flow mapping | Current network diagrams, including cloud environments and data flows, are not maintained. | Maintain current network and data-flow diagrams showing trust boundaries, cloud dependencies, and sensitive information flows. | Fail | 0 | 3 | 3 | R-004 | Document network architecture and critical data flows; define ownership and update triggers. | High | IT / Architecture | Year 1 – Q2/Q3 | Architecture visibility is foundational for segmentation, monitoring, and incident response.
GAP-004 | Identify | Asset Management | Asset classification and prioritization | Assets are not consistently classified according to sensitivity, criticality, and business value. | Apply a documented classification scheme to systems, applications, data, and services. | Fail | 1 | 3 | 2 | R-003 | Define classification criteria and apply them to the CMDB and critical service inventory. | High | IT / Business Owners | Year 1 – Q2/Q3 | Classification allows security effort to follow business importance.
GAP-005 | Identify | Governance | Cybersecurity roles and responsibilities | Oscorp relies on generalist IT support; cybersecurity roles and reporting responsibilities are not formally defined. | Document accountable cybersecurity roles, decision rights, escalation paths, and interfaces with third parties. | Fail | 0 | 3 | 3 | R-001 | Create a cybersecurity governance charter and RACI; assign accountable leadership and reporting relationships. | Critical | Executive Leadership | Year 1 – Q1 | Undefined accountability is a systemic dependency for other security initiatives.
GAP-006 | Identify | Governance | Information security policy framework | No formal information security policy framework is established. | Maintain approved security policies defining scope, responsibilities, governance, and minimum control expectations. | Fail | 0 | 3 | 3 | R-001 | Develop, approve, communicate, and periodically review core information security policies. | Critical | Executive Leadership / Security Lead | Year 1 – Q1/Q2 | Policies provide the authority and baseline for consistent control implementation.
GAP-007 | Identify | Governance | Legal and regulatory cybersecurity requirements | Cybersecurity legal and regulatory obligations are not formally documented and managed. | Maintain an applicable-requirements register and map obligations to policies, controls, and owners. | Fail | 1 | 3 | 2 | R-001 | Identify applicable obligations; assign owners; map requirements to controls and review periodically. | High | Legal / Compliance / Security | Year 1 – Q2 | Unmanaged obligations can create compliance and contractual exposure.
GAP-008 | Identify | Risk Management | Formal cybersecurity risk process | There is no established process for identifying, assessing, treating, accepting, and monitoring cybersecurity risk. | Operate a documented risk-management lifecycle with approved methodology, ownership, treatment, escalation, and review. | Fail | 0 | 3 | 3 | R-002 | Adopt the risk methodology and register; define assessment cadence, treatment criteria, and escalation. | Critical | Executive Leadership / Security Lead | Year 1 – Q1/Q2 | The risk process is the basis for prioritizing limited resources.
GAP-009 | Identify | Risk Management | Risk appetite and tolerance | Cybersecurity risk appetite and tolerance are not defined or approved. | Management should define and approve risk appetite/tolerance to guide treatment and acceptance decisions. | Fail | 0 | 3 | 3 | R-002 | Develop a cyber risk appetite statement and approval process; link thresholds to escalation and acceptance. | High | Executive Leadership | Year 1 – Q2 | Without tolerance, management cannot consistently determine acceptable residual risk.
GAP-010 | Identify | Risk Assessment | Threat, likelihood, impact, and business-impact analysis | Threat assessments and formal business impact/likelihood analysis are not consistently performed. | Risk assessments should consider threats, vulnerabilities, likelihood, business impact, and control effectiveness. | Fail | 0 | 3 | 3 | R-002 | Perform periodic cyber risk assessments and a business impact analysis using the approved methodology. | Critical | Security Lead / Business Continuity | Year 1 – Q2 | Risk scores need business-impact evidence rather than control status alone.
GAP-011 | Identify | Supply Chain | Third-party inventory and classification | Third-party interactions are handled inconsistently; suppliers are not comprehensively inventoried, classified, or tracked. | Maintain a complete supplier inventory with criticality, data access, service dependency, and security tiering. | Fail | 0 | 3 | 3 | R-005 | Create third-party inventory and tiering; identify critical vendors and security dependencies. | Critical | Procurement / Security | Year 1 – Q2/Q3 | Third parties expand Oscorp's attack surface and service dependencies.
GAP-012 | Identify | Business Environment | Critical services and resilience requirements | Critical services, dependencies, BIA results, and resilience requirements are not clearly defined. | Identify critical services and dependencies and define business-approved resilience and recovery requirements. | Fail | 1 | 3 | 2 | R-006 | Conduct a BIA; define critical services, dependencies, recovery priorities, and resilience requirements. | High | Business Continuity / IT | Year 1 – Q2/Q3 | Recovery investment should follow business criticality.
GAP-013 | Protect | Access Control | Remote access governance | Remote access controls are undefined. | Remote access should be authorized, strongly authenticated, restricted by role/device, logged, and periodically reviewed. | Fail | 0 | 3 | 3 | R-008 | Document remote-access requirements; require MFA; restrict access; log and periodically review permissions. | High | IT / IAM Owner | Year 1 – Q3 | Remote connectivity extends the security boundary and needs explicit governance.
GAP-014 | Protect | Access Control | Least privilege and separation of duties | Least privilege and separation of duties are not consistently used. | Access should be role-based, least-privileged, periodically certified, and segregated for conflicting duties. | Fail | 1 | 3 | 2 | R-007 | Implement RBAC, access reviews, privileged account separation, and separation-of-duties requirements. | Critical | IT / IAM Owner | Year 1 – Q2/Q4 | Excessive permissions increase the blast radius of compromised or misused accounts.
GAP-015 | Protect | Awareness & Training | Recurring workforce security awareness | Training is mandatory for new employees but there is no mature recurring awareness program. | Provide role-appropriate awareness at onboarding and recurring intervals, with completion tracking and updates. | Fail | 1 | 3 | 2 | R-001 | Establish annual/periodic awareness training, phishing exercises where appropriate, and completion reporting. | High | HR / Security | Year 1 – Q3 | Human risk requires ongoing reinforcement, not onboarding-only training.
GAP-016 | Protect | Awareness & Training | Privileged, executive, and third-party role training | Privileged users, executives, and third parties do not consistently receive role-specific cybersecurity training. | High-risk roles and relevant external stakeholders should understand their security responsibilities. | Fail | 1 | 3 | 2 | R-001 | Develop targeted training for privileged users, executives, and relevant third parties; document expectations contractually. | High | Security / HR / Procurement | Year 1 – Q3/Q4 | Higher-risk roles need training aligned with their authority and access.
GAP-017 | Protect | Data Security | Data at rest and in transit protection | Encryption of data at rest is not sufficiently evidenced and data in transit is not consistently encrypted. | Define and verify encryption requirements for sensitive data at rest and in transit. | Fail | 1 | 3 | 2 | R-009 | Classify sensitive data; establish encryption standards; verify implementation across local, cloud, and transmission paths. | Critical | Security / Data Owners | Year 1 – Q3/Q4 | Confidential project and business information may otherwise be exposed.
GAP-018 | Protect | Data Security | Data loss prevention | No formal data-loss prevention program is in place. | Implement proportionate controls to detect/restrict unauthorized transfer of sensitive information. | Fail | 0 | 3 | 3 | R-009 | Define DLP requirements based on data classification; implement technical and procedural controls in phases. | Critical | Security / Data Owners | Year 1 – Year 2 | Directly addresses leakage/exfiltration of sensitive information.
GAP-019 | Protect | Data Security | Asset disposal and data destruction | Asset offboarding and data disposal procedures are unclear or undocumented. | Use documented, repeatable asset disposition and secure data-destruction procedures with evidence. | Fail | 1 | 3 | 2 | R-003 | Document asset offboarding, sanitization/destruction standards, approvals, and evidence retention. | Moderate | IT Operations | Year 1 – Q4 | End-of-life assets can retain sensitive information and create inventory inaccuracies.
GAP-020 | Protect | Configuration & SDLC | Secure baseline configuration | Formal secure baseline configurations are not established. | Define approved secure baselines for relevant systems and manage exceptions. | Fail | 0 | 3 | 3 | R-010 | Create baseline standards using appropriate vendor/hardening guidance and implement configuration review. | High | IT Operations | Year 1 – Year 2 | Consistent baselines reduce preventable configuration weaknesses.
GAP-021 | Protect | Configuration & SDLC | System development lifecycle and environment separation | A formal secure SDLC and separation between development/testing and production are not established. | Security requirements should be integrated into the SDLC and production separated from non-production environments. | Fail | 0 | 3 | 3 | R-010 | Formalize SDLC security gates and segregate development, test, and production access/environments. | High | Development / IT | Year 1 – Year 2 | Weak development controls can introduce vulnerabilities directly into production.
GAP-022 | Protect | Configuration & SDLC | Configuration change control | A well-documented change-management process for technology changes is not established. | Changes should be requested, assessed, approved, tested, documented, and reviewed. | Fail | 0 | 3 | 3 | R-010 | Implement formal change control with risk/impact review, approvals, testing, rollback, and emergency-change procedures. | High | IT Operations | Year 1 – Q4 | Uncontrolled changes can cause outages and security regressions.
GAP-023 | Protect | Protective Technology | Security logging requirements | Audit/security log requirements are not formally determined, implemented, and reviewed across critical systems. | Define what must be logged, retention requirements, review responsibilities, and escalation expectations. | Fail | 0 | 3 | 3 | R-011 | Establish logging standard and onboard priority systems in phases. | Critical | Security / IT | Year 1 – Q4 | Logging is a prerequisite for effective detection and investigation.
GAP-024 | Protect | Protective Technology | Removable media and unmanaged-device controls | Policies governing removable media and outside devices are absent or unclear. | Restrict removable media and unmanaged devices according to business need and security policy. | Fail | 0 | 3 | 3 | R-009 | Define removable-media/BYOD rules; enforce device registration and technical restrictions where appropriate. | High | IT / Security | Year 1 – Q4 | Unmanaged devices can introduce malware or facilitate data loss.
GAP-025 | Detect | Anomalies & Events | Centralized SIEM and event correlation | No SIEM is operating and logs are not centrally aggregated/correlated. | Centralize relevant telemetry and correlate events against defined detection use cases. | Fail | 0 | 3 | 3 | R-011 | Implement centralized logging/SIEM in phases, beginning with critical identity, endpoint, cloud, and infrastructure sources. | Critical | Security Operations / IT | Year 2 – Q1/Q2 | Lack of correlation materially increases detection time and limits investigations.
GAP-026 | Detect | Detection Processes | Detection roles, thresholds, escalation, testing, and improvement | Cyber detection responsibilities, alert thresholds, escalation paths, testing, communication, and continuous improvement are not formally defined. | Operate documented detection processes with accountable roles, thresholds, escalation, testing, and lessons learned. | Fail | 0 | 3 | 3 | R-011 | Define detection RACI, severity/threshold criteria, triage workflow, escalation, exercises, and improvement cycle. | Critical | Security Lead / IT | Year 1 – Year 2 | Technology alone will not create an effective detection capability.
GAP-027 | Detect | Continuous Monitoring | Endpoint malware protection | No anti-malware solution is in place to evaluate or protect endpoint/server coverage. | Deploy centrally managed endpoint protection appropriate to in-scope operating systems and monitor detections. | Fail | 0 | 3 | 3 | R-012 | Deploy EDR/anti-malware; define coverage, configuration, alert handling, and health monitoring. | Critical | IT Operations / Security | Year 1 – Q4 | Endpoints are a common attack path and require a basic preventive/detective layer.
GAP-028 | Detect | Continuous Monitoring | Third-party breach/security monitoring | There is no process for collecting breach/security information from third parties. | Critical providers should have contractual notification requirements and ongoing security monitoring. | Fail | 0 | 3 | 3 | R-005 | Add breach notification and evidence requirements to contracts; monitor critical providers and reassess after incidents. | High | Procurement / Security | Year 1 – Year 2 | Vendor incidents can affect Oscorp even when internal controls are operating.
GAP-029 | Respond | Response Planning | Cybersecurity incident response plan and execution | No mature cybersecurity incident response plan or dedicated response capability is in place. | Maintain and exercise an incident response plan covering preparation, escalation, analysis, containment, eradication, recovery, and lessons learned. | Fail | 0 | 3 | 3 | R-013 | Develop IR plan, severity model, RACI, contacts, playbooks, containment/mitigation procedures, and tabletop exercises. | Critical | Security Lead / IT / Executive Leadership | Year 1 – Q3/Q4 | A security event can become materially worse when response authority and actions are undefined.
GAP-030 | Respond | Analysis | Cyber incident investigation and digital forensics | Cyber alerts are not supported by mature investigation processes or digital forensic capability. | Establish repeatable investigation, evidence handling, incident-impact analysis, and access to forensic expertise. | Fail | 0 | 3 | 3 | R-014 | Define investigation/evidence procedures and establish qualified external forensic support while internal capability matures. | High | Security Lead / Legal / IT | Year 2 – Q1/Q2 | Outsourced expertise can be more realistic than immediately building a dedicated forensic team.
GAP-031 | Respond | Mitigation | Incident containment and mitigation | Containment, mitigation, vulnerability handling, and incident prioritization are not supported by a mature response process. | Use documented containment, eradication, mitigation, and vulnerability-response procedures aligned to incident severity. | Fail | 0 | 3 | 3 | R-013 | Develop response playbooks and integrate vulnerability management with incident handling and risk acceptance. | Critical | Security Lead / IT | Year 1 – Q4 | Uncontained incidents can spread and increase operational and financial impact.
GAP-032 | Recover | Recovery Planning | Disaster recovery testing | Oscorp has a disaster recovery plan that is regularly tested. | Continue testing and maintain evidence of results, issues, and remediation. | Pass | 3 | 4 | 1 | R-015 | Preserve the existing capability and formalize evidence, metrics, and linkage to business impact requirements. | Low | Business Continuity / IT | Year 1 – Ongoing | This is an existing strength and should be sustained rather than treated as a deficiency.
GAP-033 | Recover | Improvements | Recovery lessons learned and update cycle | Lessons learned are undefined; periodic testing occurs, but an update schedule should be formalized. | Recovery plans should incorporate lessons learned and be updated through a documented review cycle. | Partial | 2 | 4 | 2 | R-015 | Add post-exercise/incident reviews, tracked actions, ownership, and a defined recovery-plan review schedule. | Moderate | Business Continuity / IT | Year 2 | Builds maturity on top of the existing tested DR capability.
GAP-034 | Recover | Communications | Crisis, executive, and reputation communications | Recovery communication/escalation, public relations, and reputation-repair responsibilities are undefined. | Maintain crisis communication procedures covering executives, internal stakeholders, external parties, and reputation management. | Fail | 0 | 3 | 3 | R-015 | Create crisis communication/escalation procedures and assign communications/PR responsibilities; exercise them with DR/IR. | High | Executive Leadership / Communications | Year 2 | Recovery is not complete if stakeholders do not receive timely, coordinated information.

## Gap Summary
Oscorp Gap Assessment Summary
NIST Function | Total Gaps | Fail | Partial | Pass | Avg Current Maturity | Avg Target Maturity | Avg Maturity Gap
Identify | 12 | 11 | 1 | 0 | 0.5 | 3 | 2.5
Protect | 12 | 12 | 0 | 0 | 0.41667 | 3 | 2.5833
Detect | 4 | 4 | 0 | 0 | 0 | 3 | 3
Respond | 3 | 3 | 0 | 0 | 0 | 3 | 3
Recover | 3 | 1 | 1 | 1 | 1.6667 | 3.6667 | 2
Portfolio Interpretation
Critical gaps | Governance, formal risk management, third-party risk, access control, data protection, centralized logging/SIEM, endpoint protection, and incident response.
Existing strength | Oscorp's disaster recovery plan is regularly tested; the gap is primarily around lessons learned, update governance, and crisis communications.
Use of maturity | Maturity scores measure distance from the desired control state; they are separate from the 1–5 likelihood/impact risk model.
Traceability | Every gap maps to a related risk ID so the assessment can flow into treatment planning and the 3-year roadmap.

## Maturity Model
Control Maturity Model
Level | Maturity | Definition
0 | Not Implemented | No control or repeatable process exists.
1 | Initial | Ad hoc, informal, incomplete, or dependent on individual effort.
2 | Developing | Partially implemented; some documentation or repeatability exists, but coverage is inconsistent.
3 | Defined | Documented, assigned, and consistently implemented across the intended scope.
4 | Managed | Measured, monitored, tested, and periodically reviewed for effectiveness.
5 | Optimized | Continuously improved, integrated, and adapted using performance and risk information.
How to use the model
Current Maturity | Score the control based on evidence in the source assessment.
Target Maturity | Choose the level appropriate to business risk and roadmap goals; not every control needs Level 5.
Maturity Gap | Target Maturity minus Current Maturity. This measures control improvement needed, not business risk severity.

## Priority Gaps
Management Priority Gaps
Priority | Gap ID | Capability | Related Risk | Recommended Action | Owner | Roadmap Phase
1 | GAP-005 | Cybersecurity roles and responsibilities | R-001 | Create a cybersecurity governance charter and RACI; assign accountable leadership and reporting relationships. | Executive Leadership | Year 1 – Q1
2 | GAP-006 | Information security policy framework | R-001 | Develop, approve, communicate, and periodically review core information security policies. | Executive Leadership / Security Lead | Year 1 – Q1/Q2
3 | GAP-008 | Formal cybersecurity risk process | R-002 | Adopt the risk methodology and register; define assessment cadence, treatment criteria, and escalation. | Executive Leadership / Security Lead | Year 1 – Q1/Q2
4 | GAP-010 | Threat, likelihood, impact, and business-impact analysis | R-002 | Perform periodic cyber risk assessments and a business impact analysis using the approved methodology. | Security Lead / Business Continuity | Year 1 – Q2
5 | GAP-011 | Third-party inventory and classification | R-005 | Create third-party inventory and tiering; identify critical vendors and security dependencies. | Procurement / Security | Year 1 – Q2/Q3
6 | GAP-014 | Least privilege and separation of duties | R-007 | Implement RBAC, access reviews, privileged account separation, and separation-of-duties requirements. | IT / IAM Owner | Year 1 – Q2/Q4
7 | GAP-017 | Data at rest and in transit protection | R-009 | Classify sensitive data; establish encryption standards; verify implementation across local, cloud, and transmission paths. | Security / Data Owners | Year 1 – Q3/Q4
8 | GAP-018 | Data loss prevention | R-009 | Define DLP requirements based on data classification; implement technical and procedural controls in phases. | Security / Data Owners | Year 1 – Year 2
9 | GAP-023 | Security logging requirements | R-011 | Establish logging standard and onboard priority systems in phases. | Security / IT | Year 1 – Q4
10 | GAP-025 | Centralized SIEM and event correlation | R-011 | Implement centralized logging/SIEM in phases, beginning with critical identity, endpoint, cloud, and infrastructure sources. | Security Operations / IT | Year 2 – Q1/Q2
11 | GAP-026 | Detection roles, thresholds, escalation, testing, and improvement | R-011 | Define detection RACI, severity/threshold criteria, triage workflow, escalation, exercises, and improvement cycle. | Security Lead / IT | Year 1 – Year 2
12 | GAP-027 | Endpoint malware protection | R-012 | Deploy EDR/anti-malware; define coverage, configuration, alert handling, and health monitoring. | IT Operations / Security | Year 1 – Q4
13 | GAP-029 | Cybersecurity incident response plan and execution | R-013 | Develop IR plan, severity model, RACI, contacts, playbooks, containment/mitigation procedures, and tabletop exercises. | Security Lead / IT / Executive Leadership | Year 1 – Q3/Q4
14 | GAP-031 | Incident containment and mitigation | R-013 | Develop response playbooks and integrate vulnerability management with incident handling and risk acceptance. | Security Lead / IT | Year 1 – Q4