## Risk Treatment Plan
Oscorp Cybersecurity Risk Treatment Plan
Risk-driven treatment plan aligned to the NIST assessment, 34-gap assessment, 1–5 risk register, and proposed three-year security program.
Risk ID | Risk Domain | Risk Title | Related Gap IDs | Treatment Strategy | Priority | Inherent Score | Inherent Rating | Treatment Objective | Treatment Actions | Treatment Owner | Risk / Executive Sponsor | Supporting Roles | Implementation Window | Required Resources / Technology | Evidence of Completion | Validation / Monitoring | Residual Likelihood | Residual Impact | Residual Score | Residual Rating | Status | Residual Risk Rationale
R-001 | Governance & Accountability | Cybersecurity governance is undefined | GAP-005; GAP-006; GAP-007; GAP-015; GAP-016 | Mitigate | Critical | 16 | High | Establish formal cybersecurity governance and accountable program leadership. | Hire Cybersecurity/GRC Manager; approve security governance charter and RACI; establish policy framework; document applicable legal/contractual requirements; launch recurring workforce and role-based security training; establish quarterly executive risk reporting. | Cybersecurity/GRC Manager | CTO / Executive Leadership | GRC Analyst; HR; Legal/Compliance | Year 1 – Q1/Q3 | Cybersecurity/GRC Manager + GRC Analyst; policy/document repository; security awareness platform or Microsoft-supported training capability; GRC platform evaluation (Drata/Oneleet). | Governance charter; approved RACI; policy approvals; training completion records; executive risk reports; requirements register. | Quarterly governance review; annual policy review; training completion/assessment metrics. | 2 | 5 | 10 | High | In Progress / Planned | Residual impact remains high because a major cyber event can still affect the enterprise even after governance improves.
R-002 | Enterprise Risk Management | Cybersecurity risk is not formally assessed or governed | GAP-008; GAP-009; GAP-010 | Mitigate | Critical | 16 | High | Implement a repeatable enterprise cybersecurity risk-management lifecycle. | Approve the 1–5 risk methodology; maintain risk register; define risk appetite/tolerance and acceptance authority; perform periodic risk assessments and BIA; establish treatment tracking and exception/escalation workflow. | Cybersecurity/GRC Manager | CTO / Executive Leadership | GRC Analyst; Business Owners | Year 1 – Q1/Q3 | GRC Analyst; current risk register/methodology; optional GRC automation platform after process design is stable. | Approved methodology; risk appetite statement; active risk register; risk acceptance records; BIA; treatment status reports. | Quarterly risk review; annual enterprise assessment; reassess after major changes/incidents. | 2 | 4 | 8 | Moderate | Planned | The process reduces unmanaged exposure but cannot eliminate the underlying business impacts represented by individual risks.
R-003 | Asset & Software Inventory | Incomplete asset and software inventory | GAP-001; GAP-002; GAP-004; GAP-019 | Mitigate | High | 16 | High | Create an authoritative and governed inventory of hardware, software, SaaS, data classifications, and asset disposition. | Expand CMDB; discover and reconcile endpoints/software; inventory SaaS; assign owners/criticality/classification; establish join/change/retire workflow; document sanitization and disposal evidence. | IT Operations | Cybersecurity/GRC Manager | Security/IAM Engineer; GRC Analyst; Business Owners | Year 1 – Q2/Q4 | Existing CMDB; Microsoft Intune/Defender device inventory where licensed; SaaS inventory process; asset-disposal service as required. | CMDB export; Intune/Defender inventory; SaaS register; ownership/classification fields; disposal certificates/logs. | Monthly reconciliation for managed assets; quarterly inventory review; annual sample audit. | 2 | 4 | 8 | Moderate | Planned | Residual risk remains where unmanaged or newly introduced assets are not immediately discovered.
R-004 | Data & Network Mapping | Critical communication and data flows are undocumented | GAP-003 | Mitigate | High | 16 | High | Document and maintain network architecture, trust boundaries, critical dependencies, and sensitive data flows. | Create current-state network/cloud diagrams; map sensitive and critical data flows; identify trust boundaries and external dependencies; establish architecture change triggers requiring diagram updates. | IT / Architecture | Cybersecurity/GRC Manager | Security/IAM Engineer; Application Owners | Year 1 – Q2/Q3 | Azure architecture tooling/documentation; diagramming platform; CMDB linkage. | Approved network diagrams; data-flow diagrams; dependency register; change tickets showing diagram updates. | Quarterly architecture review and update after material infrastructure/application changes. | 2 | 4 | 8 | Moderate | Planned | Documentation improves visibility but architecture changes can create new undocumented paths between reviews.
R-005 | Third-Party Risk | Third-party and supply-chain security is unmanaged | GAP-011; GAP-028 | Mitigate | Critical | 16 | High | Establish a risk-tiered third-party risk management program. | Inventory suppliers; classify by criticality/data access; establish due-diligence questionnaire and minimum security requirements; assess critical providers; add breach-notification/security clauses; track findings and reassess high-risk vendors. | Cybersecurity/GRC Manager / Procurement | CTO / Business Risk Owners | GRC Analyst; Legal; Procurement | Year 1 – Q2 through Year 2 | GRC/TPRM platform capability (Drata/Oneleet or equivalent) if justified; contract management repository; external ratings only if business case supports them. | Vendor inventory; tiering; completed assessments; contracts; remediation records; breach-notification clauses; reassessment schedule. | Critical vendors annually; material vendors on defined cadence; event-driven review after incidents/major changes. | 2 | 4 | 8 | Moderate | Planned | Third-party risk cannot be eliminated because Oscorp does not directly operate vendor controls.
R-006 | Business Continuity | Critical services and resilience requirements are not formally defined | GAP-012 | Mitigate | High | 16 | High | Align resilience, recovery priorities, and technology recovery objectives to business impact. | Conduct BIA; identify critical services/dependencies; define RTO/RPO and minimum service levels; map backup/recovery capability to requirements; close resilience gaps and integrate results into DR exercises. | Business Continuity / IT | CTO / Business Owners | Cybersecurity/GRC Manager; GRC Analyst; IT Operations | Year 1 – Q2/Q4 | Existing DR capability; Azure Backup/Recovery services where applicable; BIA templates/workflow. | Approved BIA; service criticality register; RTO/RPO; recovery test results; remediation actions. | Annual BIA refresh; recovery exercises at defined cadence; reassess after major service changes. | 2 | 4 | 8 | Moderate | Planned | Outages remain possible; treatment focuses on reducing duration and business consequence.
R-007 | Access Control | Least privilege and separation of duties are not consistently implemented | GAP-014 | Mitigate | Critical | 16 | High | Implement centralized identity governance using Microsoft Entra and least-privilege access practices. | Standardize identities in Microsoft Entra ID; implement RBAC; enforce MFA and Conditional Access; separate privileged accounts; use PIM/PAM capability where licensing supports it; conduct periodic access certifications; document SoD conflicts and exception approvals. | Security / IAM Engineer | Cybersecurity/GRC Manager | IT Operations; Application Owners; GRC Analyst | Year 1 – Q2/Q4 | Microsoft Entra ID; Microsoft 365/Entra licensing appropriate to required Conditional Access/PIM capabilities; Intune for device-based access signals. | Conditional Access policies; MFA reports; role assignments; PIM records; access review evidence; exception records. | Monthly privileged-access review; quarterly access certification for critical systems; annual control test. | 2 | 4 | 8 | Moderate | Planned | Identity compromise remains possible; residual impact remains high for privileged or sensitive-system compromise.
R-008 | Remote & External Access | Remote access controls are undefined | GAP-013 | Mitigate | High | 16 | High | Establish policy-driven, identity-aware remote access. | Approve remote-access standard; require Entra MFA/Conditional Access; restrict by role, device compliance, location/risk where appropriate; eliminate unmanaged legacy access; log remote authentication and review exceptions. | Security / IAM Engineer | Cybersecurity/GRC Manager | IT Operations; GRC Analyst | Year 1 – Q3/Q4 | Microsoft Entra ID; Intune device compliance; existing VPN/ZTNA capability or Azure-compatible secure access service if required. | Remote-access policy; Conditional Access configuration; device compliance reports; access logs; exception approvals. | Quarterly remote-access review; continuous authentication logging; annual policy/control test. | 2 | 4 | 8 | Moderate | Planned | Remote work inherently expands exposure, but strong identity/device controls materially reduce likelihood.
R-009 | Data Security | Encryption and data-leak protections are insufficient | GAP-017; GAP-018; GAP-024 | Mitigate | Critical | 16 | High | Protect sensitive information through classification, encryption, DLP, and device/media controls. | Define data classification; require encryption at rest/in transit; manage keys/secrets appropriately; implement Microsoft Purview DLP/information protection where suitable; restrict removable media/unmanaged devices; monitor high-risk data movement. | Cybersecurity/GRC Manager / Data Owners | CTO / Business Data Owners | Security Engineer; GRC Analyst; IT Operations | Year 1 – Q3 through Year 2 | Microsoft Purview capabilities as justified; Azure Key Vault for applicable cloud keys/secrets; Microsoft Defender/Intune device controls; encryption native to Azure/Microsoft platforms. | Classification standard; encryption configuration evidence; DLP policies/alerts; key-management records; removable-media policy; test results. | Quarterly DLP review; annual data-control assessment; continuous monitoring of applicable alerts. | 2 | 4 | 8 | Moderate | Planned | Encryption/DLP reduce exposure and sometimes impact, but authorized users and novel exfiltration paths remain residual concerns.
R-010 | Secure Configuration & Change Management | Configuration, SDLC, and environment separation controls are immature | GAP-020; GAP-021; GAP-022 | Mitigate | High | 16 | High | Create secure configuration, change-management, and secure-development control baselines. | Define hardened baselines; manage endpoints with Intune/security policies; formalize change control; separate dev/test/prod; introduce security requirements and review gates into SDLC; document exceptions and rollback procedures. | IT Operations / Development | Cybersecurity/GRC Manager | Security Engineer; Development Leads; GRC Analyst | Year 1 – Q4 through Year 2 | Microsoft Intune; Defender for Cloud for Azure/cloud posture where justified; CI/CD security tooling native to development platform; change-management/ticketing system. | Baseline standards; configuration reports; approved changes; environment access evidence; SDLC checklists; exception records. | Monthly configuration compliance review; quarterly change-control sample; annual SDLC control test. | 2 | 4 | 8 | Moderate | Planned | Configuration drift and software defects remain possible even with controlled processes.
R-011 | Security Monitoring | Oscorp lacks centralized security monitoring and event correlation | GAP-023; GAP-025; GAP-026 | Mitigate | Critical | 20 | Very High | Build centralized logging, detection engineering, and monitored security operations. | Define logging standard; prioritize identity/endpoint/cloud/application sources; deploy Microsoft Sentinel after log requirements and ownership are defined; build detection use cases and severity thresholds; integrate MDR/MSSP for after-hours coverage if internal staffing is insufficient; tune and test detections. | Security Analyst / Security Operations | Cybersecurity/GRC Manager | Security Engineer; IT Operations; MDR/MSSP | Year 1 – Q4 through Year 2 – Q2 | Microsoft Sentinel; Log Analytics/Azure monitoring consumption; MDR/MSSP as required; Microsoft Defender telemetry. | Logging standard; source onboarding list; Sentinel dashboards/rules; alert tickets; detection tests; MDR reports; escalation records. | Continuous monitoring; monthly detection tuning; quarterly use-case testing; annual program effectiveness review. | 2 | 5 | 10 | High | Planned | Central monitoring lowers likelihood/dwell time but cannot prevent all incidents; high-impact events remain possible.
R-012 | Malware & Endpoint Security | Endpoint protection and malicious-code detection are inadequate | GAP-027 | Mitigate | Critical | 16 | High | Deploy centrally managed endpoint prevention, detection, and response. | Deploy Microsoft Defender for Business/Endpoint as appropriate; ensure endpoint coverage; configure protection policies; integrate with Intune; establish alert triage and isolation process; monitor agent health and exclusions. | Security Engineer / IT Operations | Cybersecurity/GRC Manager | Security Analyst; Help Desk | Year 1 – Q3/Q4 | Microsoft Defender endpoint capability; Microsoft Intune; Microsoft Sentinel integration when available. | Coverage dashboard; protection policies; alert/incident records; isolation tests; health/exclusion reports. | Continuous agent-health monitoring; monthly coverage review; quarterly endpoint-control test. | 2 | 4 | 8 | Moderate | Planned | Endpoint controls substantially reduce common malware risk but do not eliminate zero-days, misuse, or compromised credentials.
R-013 | Incident Response | Incident response roles, procedures, escalation, and containment are undefined | GAP-029; GAP-031 | Mitigate | Critical | 20 | Very High | Establish and exercise a complete cybersecurity incident-response capability. | Develop IR plan and RACI; define severity and escalation criteria; create playbooks for common scenarios; define containment/eradication/recovery actions; establish executive/legal/communications contacts; integrate Sentinel/Defender alerts; conduct tabletop exercises and track lessons learned. | Cybersecurity/GRC Manager | CTO / Executive Leadership | Security Analyst; Security Engineer; Legal; Communications; IT | Year 1 – Q2/Q4 | Internal security team; Microsoft Defender/Sentinel; incident ticketing/case management; external IR retainer for major events. | Approved IR plan; playbooks; contact/escalation list; tabletop records; incident tickets; lessons-learned actions. | Two tabletop exercises per year initially; review after every material incident; annual full plan review. | 2 | 5 | 10 | High | Planned | Strong response reduces duration and spread, but severe incidents can still create enterprise-level impact.
R-014 | Digital Forensics & Investigation | Incident investigation and forensic capability is limited | GAP-030 | Mitigate / Transfer | High | 16 | High | Establish repeatable investigation/evidence handling and retain specialist forensic capability. | Define investigation and chain-of-custody procedures; preserve relevant logs; train internal analysts on evidence handling; establish external DFIR retainer/SOW for complex incidents; test escalation and evidence-transfer procedures. | Cybersecurity/GRC Manager / Legal | CTO | Security Analyst; Security Engineer; External DFIR Provider | Year 2 – Q1/Q2 | External DFIR retainer; Sentinel/Defender evidence sources; secure evidence storage; forensic tooling primarily through specialist provider unless volume justifies internal purchase. | Investigation SOP; chain-of-custody form; DFIR contract; exercise evidence; incident investigation reports. | Annual provider review/exercise; review evidence procedures after incidents or technology changes. | 2 | 4 | 8 | Moderate | Planned | Specialist outsourcing is cost-effective, but response time and provider dependency remain residual risks.
R-015 | Recovery & Crisis Communications | Recovery communications, reputation management, and lessons learned are incomplete | GAP-032; GAP-033; GAP-034 | Mitigate | High | 12 | Moderate | Preserve the tested DR capability while formalizing lessons learned and crisis communications. | Maintain DR testing; require post-exercise/incident lessons learned; track corrective actions; define executive/internal/external crisis communications; assign PR/reputation roles; align communication exercises with IR/DR scenarios. | Business Continuity / Communications | CTO / Executive Leadership | Cybersecurity/GRC Manager; GRC Analyst; IT Operations | Year 2 – Year 3 | Existing DR tooling; Azure Backup/Recovery where applicable; crisis communication tools already used by the business where adequate; external PR support if required. | DR test reports; lessons-learned register; corrective actions; crisis communication plan; exercise records. | Annual recovery exercise minimum; lessons-learned review after each test/incident; annual communications exercise. | 2 | 3 | 6 | Moderate | Planned | The tested DR plan is an existing strength; remaining exposure centers on coordination, communications, and evolving dependencies.

## Treatment Summary
Risk Treatment Summary
Phase | Primary Objective | Key Risks | Key Gap Areas | People / Ownership | Technology / Services | Primary Evidence | Expected Outcome
Year 1 – Q1/Q2 | Establish governance and risk management | R-001; R-002 | Governance, policies, risk methodology, risk appetite, BIA initiation | Hire Cybersecurity/GRC Manager and GRC Analyst; CTO executive sponsor | GRC platform evaluation only after core process design | Governance charter, RACI, policies, risk methodology/register | Accountable security program and repeatable risk decisions
Year 1 – Q2/Q4 | Build foundational protection | R-003; R-004; R-006; R-007; R-008; R-009; R-012; R-013 | Inventory, architecture, IAM, remote access, data protection, endpoint, IR | Security/IAM Engineer + Security Analyst join team | Microsoft Entra, Intune, Defender; Purview/Key Vault as justified; IR retainer | Inventory, CA/MFA, access reviews, endpoint coverage, IR plan/tabletop | Reduced attack surface and established response capability
Year 2 – Q1/Q2 | Centralize detection and investigation | R-010; R-011; R-014 | Secure configuration, logging, SIEM, detection, forensics | Security team matures; add SOC capacity and/or MDR | Microsoft Sentinel, Azure monitoring/Log Analytics, MDR/MSSP, external DFIR | Log source coverage, detection rules/tests, investigation procedures | Improved detection, triage, evidence preservation and escalation
Year 2 – Year 3 | Mature assurance and resilience | R-005; R-009; R-010; R-015 | TPRM, DLP, SDLC, recovery improvement, crisis communications | GRC and technical functions specialize; business owners increasingly accountable | GRC automation if justified; cloud posture/security tooling; recovery services | Vendor reassessments, DLP tests, SDLC evidence, DR/IR exercises | Controls become measurable, repeatable, and auditable

## Treatment Methodology
Risk Treatment Methodology
Element | Definition | How Used in This Plan | Governance Rule
Mitigate | Implement controls that reduce likelihood and/or impact. | Primary treatment for most Oscorp risks because the assessment shows material control deficiencies. | Treatment is not complete until implementation evidence and operating effectiveness are validated.
Transfer | Shift a defined portion of exposure to a qualified third party. | Used with DFIR/MDR and may apply to other specialist services or insurance. | Transfer does not remove Oscorp's accountability or all residual risk.
Accept | Formally retain risk when further treatment is not justified. | May be used for residual risks after management evaluates cost, impact, and risk appetite. | Material acceptance requires documented business-owner and executive approval.
Avoid | Stop the activity creating the risk. | Reserved for cases where risk exceeds tolerance and cannot be economically reduced. | Requires business decision and documented impact assessment.
Residual Risk | Risk expected to remain after proposed treatment is successfully implemented. | Uses the same 1–5 likelihood and impact model as the risk register. | Residual values are estimates until controls are implemented and tested.
Control Validation | Evidence-based confirmation that a treatment is implemented and operating. | Evidence and monitoring fields specify how each treatment will be verified. | Do not close a risk solely because a tool was purchased or a policy was written.
Technology Fit | Technology must address a defined gap and be supported by people/process. | Microsoft Entra/Intune/Defender/Sentinel and GRC/MDR/DFIR services are tied to specific gaps. | A platform supports compliance; it does not by itself make Oscorp NIST-aligned.

## Validation & Evidence
Treatment Validation & Evidence Checklist
Risk ID | Validation Focus | Minimum Evidence | Control Test | Review Cadence | Closure Standard
R-001 | Establish formal cybersecurity governance and accountable program leadership. | Governance charter; approved RACI; policy approvals; training completion records; executive risk reports; requirements register. | Quarterly governance review; annual policy review; training completion/assessment metrics. | Per treatment plan / after material change | Treatment implemented, evidence retained, control tested, residual risk reassessed, and risk owner approves status.
R-002 | Implement a repeatable enterprise cybersecurity risk-management lifecycle. | Approved methodology; risk appetite statement; active risk register; risk acceptance records; BIA; treatment status reports. | Quarterly risk review; annual enterprise assessment; reassess after major changes/incidents. | Per treatment plan / after material change | Treatment implemented, evidence retained, control tested, residual risk reassessed, and risk owner approves status.
R-003 | Create an authoritative and governed inventory of hardware, software, SaaS, data classifications, and asset disposition. | CMDB export; Intune/Defender inventory; SaaS register; ownership/classification fields; disposal certificates/logs. | Monthly reconciliation for managed assets; quarterly inventory review; annual sample audit. | Per treatment plan / after material change | Treatment implemented, evidence retained, control tested, residual risk reassessed, and risk owner approves status.
R-004 | Document and maintain network architecture, trust boundaries, critical dependencies, and sensitive data flows. | Approved network diagrams; data-flow diagrams; dependency register; change tickets showing diagram updates. | Quarterly architecture review and update after material infrastructure/application changes. | Per treatment plan / after material change | Treatment implemented, evidence retained, control tested, residual risk reassessed, and risk owner approves status.
R-005 | Establish a risk-tiered third-party risk management program. | Vendor inventory; tiering; completed assessments; contracts; remediation records; breach-notification clauses; reassessment schedule. | Critical vendors annually; material vendors on defined cadence; event-driven review after incidents/major changes. | Per treatment plan / after material change | Treatment implemented, evidence retained, control tested, residual risk reassessed, and risk owner approves status.
R-006 | Align resilience, recovery priorities, and technology recovery objectives to business impact. | Approved BIA; service criticality register; RTO/RPO; recovery test results; remediation actions. | Annual BIA refresh; recovery exercises at defined cadence; reassess after major service changes. | Per treatment plan / after material change | Treatment implemented, evidence retained, control tested, residual risk reassessed, and risk owner approves status.
R-007 | Implement centralized identity governance using Microsoft Entra and least-privilege access practices. | Conditional Access policies; MFA reports; role assignments; PIM records; access review evidence; exception records. | Monthly privileged-access review; quarterly access certification for critical systems; annual control test. | Per treatment plan / after material change | Treatment implemented, evidence retained, control tested, residual risk reassessed, and risk owner approves status.
R-008 | Establish policy-driven, identity-aware remote access. | Remote-access policy; Conditional Access configuration; device compliance reports; access logs; exception approvals. | Quarterly remote-access review; continuous authentication logging; annual policy/control test. | Per treatment plan / after material change | Treatment implemented, evidence retained, control tested, residual risk reassessed, and risk owner approves status.
R-009 | Protect sensitive information through classification, encryption, DLP, and device/media controls. | Classification standard; encryption configuration evidence; DLP policies/alerts; key-management records; removable-media policy; test results. | Quarterly DLP review; annual data-control assessment; continuous monitoring of applicable alerts. | Per treatment plan / after material change | Treatment implemented, evidence retained, control tested, residual risk reassessed, and risk owner approves status.
R-010 | Create secure configuration, change-management, and secure-development control baselines. | Baseline standards; configuration reports; approved changes; environment access evidence; SDLC checklists; exception records. | Monthly configuration compliance review; quarterly change-control sample; annual SDLC control test. | Per treatment plan / after material change | Treatment implemented, evidence retained, control tested, residual risk reassessed, and risk owner approves status.
R-011 | Build centralized logging, detection engineering, and monitored security operations. | Logging standard; source onboarding list; Sentinel dashboards/rules; alert tickets; detection tests; MDR reports; escalation records. | Continuous monitoring; monthly detection tuning; quarterly use-case testing; annual program effectiveness review. | Per treatment plan / after material change | Treatment implemented, evidence retained, control tested, residual risk reassessed, and risk owner approves status.
R-012 | Deploy centrally managed endpoint prevention, detection, and response. | Coverage dashboard; protection policies; alert/incident records; isolation tests; health/exclusion reports. | Continuous agent-health monitoring; monthly coverage review; quarterly endpoint-control test. | Per treatment plan / after material change | Treatment implemented, evidence retained, control tested, residual risk reassessed, and risk owner approves status.
R-013 | Establish and exercise a complete cybersecurity incident-response capability. | Approved IR plan; playbooks; contact/escalation list; tabletop records; incident tickets; lessons-learned actions. | Two tabletop exercises per year initially; review after every material incident; annual full plan review. | Per treatment plan / after material change | Treatment implemented, evidence retained, control tested, residual risk reassessed, and risk owner approves status.
R-014 | Establish repeatable investigation/evidence handling and retain specialist forensic capability. | Investigation SOP; chain-of-custody form; DFIR contract; exercise evidence; incident investigation reports. | Annual provider review/exercise; review evidence procedures after incidents or technology changes. | Per treatment plan / after material change | Treatment implemented, evidence retained, control tested, residual risk reassessed, and risk owner approves status.
R-015 | Preserve the tested DR capability while formalizing lessons learned and crisis communications. | DR test reports; lessons-learned register; corrective actions; crisis communication plan; exercise records. | Annual recovery exercise minimum; lessons-learned review after each test/incident; annual communications exercise. | Per treatment plan / after material change | Treatment implemented, evidence retained, control tested, residual risk reassessed, and risk owner approves status.