## Risk Register
Oscorp NIST CSF Risk Register
Built from the GRC Mastery NIST Cyber Security Assessment (2026) ¦ Portfolio artifact ¦ Risk scores and proposed residual ratings are analytical estimates
Risk ID | Risk Area | Risk Title | Risk Description | Primary Impact | Inherent Likelihood | Inherent Impact | Inherent Score | Treatment | Treatment Plan | Risk Owner | NIST CSF Function | NIST CSF Category | Residual Likelihood | Residual Impact | Residual Rating | Residual Score | Priority | Target | Business Rationale | Residual Likelihood | Residual Impact
R-001 | Governance & Accountability | Cybersecurity governance is undefined | Oscorp lacks a formal cybersecurity governance structure, defined security roles, documented policies, and a clear reporting/oversight chain. This can cause accountability gaps and inconsistent security decisions. | Governance / Confidentiality / Integrity / Availability | High | High | 16 | Mitigate | Establish an information security governance charter; define security roles and responsibilities; appoint accountable leadership; create core policies; establish management/board reporting and risk acceptance authority. | Executive Leadership / Security Lead | Identify | ID.GV-1, ID.GV-2, ID.GV-4 | Low | Very High | High | 10 | Critical | Year 1 – Q1/Q2 | Directly affects the organization's ability to manage every other cybersecurity risk. | Low | Very High
R-002 | Enterprise Risk Management | Cybersecurity risk is not formally assessed or governed | Oscorp has no established cybersecurity risk-management process, formal risk tolerance, or documented method for using threats, vulnerabilities, likelihood, and business impact to determine risk. | Confidentiality / Integrity / Availability | High | High | 16 | Mitigate | Define risk methodology, risk appetite/tolerance, assessment cadence, risk register, treatment criteria, and formal risk acceptance/escalation process. | Executive Leadership / Security Lead | Identify | ID.RA-4, ID.RA-6, ID.RM-1, ID.RM-2, ID.RM-3 | Low | High | Moderate | 8 | Critical | Year 1 – Q1/Q2 | A formal risk process is the foundation for prioritizing limited security resources. | Low | High
R-003 | Asset & Software Inventory | Incomplete asset and software inventory | The CMDB exists but does not fully cover hardware, software, SaaS, or critical applications, and there is no established recurring review process. Unknown assets can remain unprotected or unsupported. | Confidentiality / Integrity / Availability | High | High | 16 | Mitigate | Expand the authoritative inventory; include hardware, software, SaaS and critical applications; assign owners/classifications; reconcile inventory on a defined schedule. | IT Operations | Identify | ID.AM-1, ID.AM-2, ID.AM-4, ID.AM-5 | Low | High | Moderate | 8 | High | Year 1 – Q2 | You cannot reliably protect, monitor, patch, or recover assets you cannot identify. | Low | High
R-004 | Data & Network Mapping | Critical communication and data flows are undocumented | Oscorp lacks current network diagrams and documented communication/data flows, including cloud environments. This limits visibility into trust boundaries, sensitive data movement, and potential attack paths. | Confidentiality / Integrity | High | High | 16 | Mitigate | Create and maintain network and data-flow diagrams; identify trust boundaries, critical systems, cloud dependencies, and sensitive information flows. | IT Operations / Architecture | Identify | ID.AM-3 | Low | High | Moderate | 8 | High | Year 1 – Q2/Q3 | Improves architecture visibility and supports segmentation, monitoring, and incident response. | Low | High
R-005 | Third-Party Risk | Third-party and supply-chain security is unmanaged | Third-party interactions are handled inconsistently, suppliers are not comprehensively inventoried or classified, and there is no defined process for collecting supplier security or breach information. | Confidentiality / Integrity / Availability | High | High | 16 | Mitigate | Create a third-party inventory and tiering model; assess critical suppliers; establish contractual security requirements; track security reviews, incidents, and evidence such as SOC reports where appropriate. | Procurement / Security | Identify | ID.SC-1, ID.SC-2, ID.SC-3, ID.SC-4 | Low | High | Moderate | 8 | Critical | Year 1 – Q2/Q4 | Third parties can materially expand the attack surface and introduce risks outside direct organizational control. | Low | High
R-006 | Business Continuity | Critical services and resilience requirements are not formally defined | Critical services, dependencies, business impacts, and resilience requirements are not sufficiently documented or prioritized for cybersecurity decision-making. | Availability | High | High | 16 | Mitigate | Perform a business impact analysis; identify critical services/dependencies; define recovery priorities and resilience requirements; align BCP/DR objectives with business needs. | Business Continuity / IT | Identify | ID.BE-4, ID.BE-5, ID.BE-6 | Low | High | Moderate | 8 | High | Year 1 – Q2/Q3 | Recovery priorities should be driven by business impact rather than technology assumptions. | Low | High
R-007 | Access Control | Least privilege and separation of duties are not consistently implemented | Access permissions are not managed using least privilege and separation of duties, while privileged access controls are incomplete. This increases the impact of compromised or misused accounts. | Confidentiality / Integrity | High | High | 16 | Mitigate | Implement role-based access; perform periodic access reviews; separate privileged accounts; define privileged access standards; enforce least privilege and separation of duties for critical functions. | IT / IAM Owner | Protect | PR.AC-4, PR.AC-6 | Low | High | Moderate | 8 | Critical | Year 1 – Q2/Q4 | Excessive permissions can turn a single compromised account into a broader security incident. | Low | High
R-008 | Remote & External Access | Remote access controls are undefined | Remote access is not clearly governed by documented controls, creating uncertainty around authentication, authorization, device requirements, and monitoring for external connections. | Confidentiality / Integrity | High | High | 16 | Mitigate | Document remote-access requirements; enforce MFA; restrict access based on role/device/risk; log remote connections; periodically review remote-access permissions. | IT / IAM Owner | Protect | PR.AC-7 | Low | High | Moderate | 8 | High | Year 1 – Q3 | Remote access can bypass traditional network boundaries and requires explicit security controls. | Low | High
R-009 | Data Security | Encryption and data-leak protections are insufficient | Assessment findings indicate gaps in protection of data at rest and in transit, as well as a lack of formal data-leak prevention controls. Sensitive information may therefore be exposed or exfiltrated. | Confidentiality | High | High | 16 | Mitigate | Classify sensitive data; define encryption requirements; verify cloud/provider encryption; implement appropriate DLP controls; restrict removable media and data sharing based on risk. | Security / Data Owners | Protect | PR.DS-1, PR.DS-2, PR.DS-5, PR.DS-6, PR.DS-7 | Low | High | Moderate | 8 | Critical | Year 1 – Q3/Q4 | This is one of the most direct paths to loss of confidential information. | Low | High
R-010 | Secure Configuration & Change Management | Configuration, SDLC, and environment separation controls are immature | Oscorp lacks formal baseline configurations, configuration change control, a defined SDLC, and separation between development/testing and production environments. | Integrity / Availability | High | High | 16 | Mitigate | Define secure configuration baselines; implement change control; formalize SDLC security requirements; separate development/test/production environments; document exceptions. | IT Operations / Development | Protect | PR.IP-1, PR.IP-2, PR.IP-3, PR.IP-7 | Low | High | Moderate | 8 | High | Year 1 – Year 2 | Weak configuration and change controls can introduce vulnerabilities directly into production. | Low | High
R-011 | Security Monitoring | Oscorp lacks centralized security monitoring and event correlation | There is no operating SIEM, limited/no centralized logging, no defined cyber detection roles, and no established alert thresholds or escalation process. Malicious activity may therefore remain undetected. | Confidentiality / Integrity / Availability | Very High | High | 20 | Mitigate | Define logging requirements; centralize critical security logs; implement SIEM capability; establish detection use cases, alert thresholds, triage procedures, escalation paths, and monitoring ownership. | Security Operations / IT | Detect | DE.AE-1, DE.AE-2, DE.AE-3, DE.AE-4, DE.AE-5, DE.CM-1, DE.CM-7 | Low | Very High | High | 10 | Critical | Year 2 – Q1/Q2 | The absence of centralized detection substantially increases dwell time and limits incident investigation. | Low | Very High
R-012 | Malware & Endpoint Security | Endpoint protection and malicious-code detection are inadequate | The assessment indicates no anti-malware solution is in place and no defined capability for detecting malicious code or unauthorized mobile code. | Confidentiality / Integrity / Availability | High | High | 16 | Mitigate | Deploy centrally managed endpoint protection/EDR appropriate to the environment; define coverage requirements; monitor detections; establish response procedures for compromised endpoints. | IT Operations / Security | Protect / Detect | PR.PT-4, DE.CM-4 | Low | High | Moderate | 8 | Critical | Year 1 – Q4 | Endpoint controls provide a practical first line of defense while broader monitoring capabilities mature. | Low | High
R-013 | Incident Response | Incident response roles, procedures, escalation, and containment are undefined | Oscorp has no mature cyber incident response process or dedicated response capability. Personnel, escalation, incident categorization, containment, mitigation, and external coordination are not consistently defined or tested. | Confidentiality / Integrity / Availability | Very High | High | 20 | Mitigate | Develop an incident response plan; define roles/RACI and escalation thresholds; establish severity categories; document containment and mitigation procedures; identify external contacts; conduct tabletop exercises. | Security Lead / IT / Executive Leadership | Respond | RS.RP-1, RS.CO-1, RS.CO-2, RS.CO-3, RS.CO-4, RS.MI-1, RS.MI-2 | Low | Very High | High | 10 | Critical | Year 1 – Q3/Q4 | A security event becomes significantly more damaging when the organization does not know who acts, when, or how. | Low | Very High
R-014 | Digital Forensics & Investigation | Incident investigation and forensic capability is limited | Oscorp lacks a digital forensics team and has no mature process for investigating cyber alerts, understanding incident impact, or preserving evidence. | Confidentiality / Integrity / Availability | High | High | 16 | Mitigate | Define an investigation and evidence-handling process; identify internal capability gaps; establish external forensic support where appropriate; integrate investigation procedures with incident response. | Security Lead / Legal / IT | Respond | RS.AN-1, RS.AN-2, RS.AN-3, RS.AN-4 | Low | High | Moderate | 8 | High | Year 2 – Q1/Q2 | External support can be more realistic than building a dedicated forensic team immediately. | Low | High
R-015 | Recovery & Crisis Communications | Recovery communications, reputation management, and lessons learned are incomplete | Oscorp has a tested disaster recovery plan, but recovery lessons learned, communications/escalation, public relations, and reputation-repair activities are not clearly defined. | Availability / Reputation | Moderate | High | 12 | Mitigate | Add lessons-learned requirements to recovery; define internal/executive communications and escalation; establish crisis communications and public-relations responsibilities; update recovery plans after exercises/incidents. | Business Continuity / Communications / Executive Leadership | Recover | RC.IM-1, RC.IM-2, RC.CO-1, RC.CO-2 | Low | Moderate | Moderate | 6 | High | Year 2 – Year 3 | The existing DR strength should be preserved while adding governance and communications around recovery. | Low | Moderate

## Assessment Summary
Assessment-Derived Summary
Source Workbook | GRC Mastery NIST Cyber Security Assessment_2026.xlsx
NIST Function | Non-Pass / Unknown | Pass | Total Findings | Current Pass Rate
Identify | 21 | 3 | 24 | 12.5%
Protect | 26 | 9 | 35 | 25.71%
Detect | 15 | 3 | 18 | 16.67%
Respond | 15 | 0 | 15 | 0%
Recover | 4 | 2 | 6 | 33.33%
Key interpretation | The assessment shows the largest concentration of deficiencies in Protect, Detect, and Respond, with governance/risk-management weaknesses in Identify acting as systemic drivers.

## Scoring Methodology
Risk Scoring Methodology — 1–5 Model
Likelihood | Value | Working Definition | Impact | Value | Working Definition
Very Low | 1 | Rare or minimal exposure; occurrence is not expected under normal conditions. | Very Low | 1 | Negligible business or security consequence.
Low | 2 | Unlikely, but a credible scenario exists. | Low | 2 | Limited operational or informational impact.
Moderate | 3 | Reasonably possible under current conditions. | Moderate | 3 | Material impact to a business process, asset, or stakeholder.
High | 4 | Likely to occur or significant/recurring exposure exists. | High | 4 | Significant operational, financial, regulatory, or reputational impact.
Very High | 5 | Highly likely, broadly exposed, or persistent exposure exists. | Very High | 5 | Severe enterprise-level impact or major loss of critical information/services.
Rating | Likelihood × Impact |  | Residual Risk | Approach | Meaning
Low | 1–4 |  | Residual Likelihood | 1–5 | Expected likelihood after proposed controls are implemented.
Moderate | 5–9 |  | Residual Impact | 1–5 | Expected impact after proposed controls are implemented.
High | 10–16 |  | Residual Score | Likelihood × Impact | Calculated from the two residual parameters.
Critical | 17–25 |  | Validation | Required | Residual ratings remain estimates until control effectiveness is tested.

## Risk Traceability
Risk ID | Source NIST Function | Source Control Description / Finding | Assessment Status | Assessment Comment / Evidence | How Converted to Risk
R-001 | Identify | Organizational information security policy is established. | Fail | No information security policy; roles/reporting chain undefined. | Governance risk
R-002 | Identify | Governance and risk management processes address cybersecurity risk. | Fail | No established cyber risk process or defined stakeholders. | Enterprise risk risk
R-003 | Identify | Software platforms and applications within the organization are inventoried. | Fail | SaaS/local applications are not comprehensively managed; no regular review. | Asset inventory risk
R-004 | Identify | Organizational communication and data flows are mapped. | Fail | No current network/data-flow mapping. | Architecture/data-flow risk
R-005 | Identify | The organization’s role in the supply chain is identified and communicated. | Fail | Third-party interactions are handled inconsistently; suppliers not classified/tracked. | Third-party risk
R-006 | Identify | Dependencies and critical functions for delivery of critical services are established. | Fail | Critical services/dependencies not formally identified; BIA needed. | Business continuity risk
R-007 | Protect | Access permissions are managed, incorporating least privilege and separation of duties. | Fail | Least privilege and separation of duties are not used; privileged access incomplete. | Access-control risk
R-008 | Protect | Remote access is managed. | Fail | Remote access controls are undefined. | Remote-access risk
R-009 | Protect | Data-at-rest/data-in-transit protections and data-leak controls. | Fail | Encryption/DLP protections are incomplete or absent. | Data protection risk
R-010 | Protect | Baseline configuration, SDLC, and configuration change controls are in place. | Fail | Formal configuration/SDLC/change controls and environment separation are absent. | Change/configuration risk
R-011 | Detect | Event data are aggregated and correlated from multiple sources and sensors. | Fail | No SIEM and no centralized logs; detection roles/processes undefined. | Detection/monitoring risk
R-012 | Detect | Malicious code is detected. | Fail | No anti-malware solution or defined malicious-code detection capability. | Endpoint/malware risk
R-013 | Respond | Response plan, communications, analysis, mitigation and incident categorization. | Fail | No mature cyber IR plan/team; containment and escalation are undefined. | Incident-response risk
R-014 | Respond | Forensics are performed. | Fail | No digital forensics team; cyber-alert investigation capability is limited. | Investigation risk
R-015 | Recover | Recovery communications, reputation repair, and lessons learned. | Fail | Recovery lessons learned, communications, PR, and escalation are undefined; DR testing itself passes. | Recovery governance risk

## Roadmap Priorities
Priority | Risk ID | Initiative | Reason for Timing | Target
1 | R-001 | Establish cybersecurity governance, policy, roles, and reporting | Governance is a systemic dependency for all other controls. | Year 1 – Q1/Q2
2 | R-002 | Implement enterprise cyber risk methodology and risk register | Creates the decision framework for prioritizing resources and accepting residual risk. | Year 1 – Q1/Q2
3 | R-007 | Implement least privilege, access reviews, and privileged access controls | High-impact exposure that can be reduced with policy/process and targeted technology. | Year 1 – Q2/Q4
4 | R-003 | Complete asset/software/SaaS inventory and classification | Enables reliable protection, monitoring, patching, and recovery. | Year 1 – Q2
5 | R-005 | Establish third-party risk management | Supplier exposure is currently unmanaged and can introduce external compromise paths. | Year 1 – Q2/Q4
6 | R-009 | Protect sensitive data with encryption and DLP controls | Directly addresses confidentiality risk and potential data leakage. | Year 1 – Q3/Q4
7 | R-013 | Build and test incident response capability | Reduces business impact when preventive controls fail. | Year 1 – Q3/Q4
8 | R-011 | Implement centralized logging/SIEM and detection use cases | Major maturity uplift; scheduled after foundational governance and asset visibility. | Year 2 – Q1/Q2
9 | R-012 | Deploy managed endpoint protection/EDR | Practical detection/prevention layer while SIEM capability matures. | Year 1 – Q4
10 | R-010 | Formalize secure configuration, SDLC, change control, and environment separation | Reduces recurring weaknesses introduced through technology change. | Year 1 – Year 2
11 | R-006 | Perform BIA and define critical-service resilience requirements | Makes continuity and recovery investment business-driven. | Year 1 – Q2/Q3
12 | R-014 | Establish forensic investigation capability | Can be outsourced initially; mature as detection/response capabilities increase. | Year 2 – Q1/Q2
13 | R-015 | Formalize recovery communications and lessons learned | Builds on the existing tested DR capability. | Year 2 – Year 3